## Dashboard
Broad compatibility plan v4 - OpenAudio BeBoB MAFW, OS X 10.9 to macOS 15 (Legacy 10.6.8-10.8.5 dropped, R130)
2026-10-21 (R129) - Modern edition works on macOS 14.8.9 Intel (Audiophile); Classic + Modern 0.3.0 packages built; DEC-5, DEC-9, DEC-10 answered. Legacy and Apple Silicon not started. 2026-10-21 - DEC-5 answered: three editions (Legacy / Classic / Modern); Modern Intel in progress on the dev Mac (loads and plays, R126); plan: BROAD_COMPATIBILITY_PLAN_v2.md
Short answer
One package / one version for 10.6.8-15 | Yes, feasible (no checked fact forbids it)
One binary per component | No: kernel symbol generations (E-1, E-2), arm64e kext (E-6), Swift floor 10.9 (E-11)
Kernel-extension builds in the package | 2: Legacy (i386 + x86_64, 10.6 SDK) and Main (x86_64 10.13 SDK + arm64e 15 SDK in one file); 1 if U-12 holds
As separate downloads | Decided (DEC-5, user 2026-10-21): 3 editions - Legacy 10.6.8-10.8.5, Classic 10.9-10.15, Modern 11-15 (Intel, Apple Silicon later); plan v2 §11a
What older OSes lose | No audio / mixer / MIDI function expected; panel cosmetics on 10.6-10.8 (Feature_by_OS), or the whole panel if DEC-4 = c
Recommendation | Stage it: S1 (Intel 10.9-15), then S2 (Apple Silicon, needs hardware), S3 (10.6.8-10.8.5) only if wanted
Effort by band (sessions; refreshes from Tasks)
Band | Meaning | Tasks | Min | Max | Done / partly
C | Common
M | Intel 10.9-15
AS | Apple Silicon 11-15
L | 10.6.8-10.8.5 (DROPPED 2026-10-22)
Total
Effort by scenario (sessions)
Scenario | Covers | Bands | Min | Max
S1 | Intel 10.9-15 | C + M
S2 | S1 + Apple Silicon 11-15 | C + M + AS
S3 | WITHDRAWN (Legacy dropped) | C + M + AS + L
S1 + L | All Intel 10.6.8-15, no Apple Silicon | C + M + L
Includes the on-device checks (BC-6), which run only on request: M 2, AS 1-2, L 1-2 sessions.
Status
Decisions open
Decisions answered
Tasks waiting for a decision
Tasks done or partly done (static)
On-device tasks (on request / blocked)
Evidence checked (E-n)
Claims still unverified (U-n)
Key findings of 2026-10-21
E-1/E-2: the 0.2.2 kext imports _IOLockSleep_darwin14, _IOLockWakeup_darwin14 and IOService::configureReport/updateReport - names old kernels lack, so 10.6-10.8 need an old-SDK build.
E-4: on macOS 14.8.4 Intel, 775 of the 777 imports are defined; the 2 others are reserved IOAudioEngine slots 15/16 (U-11).
E-5: the FireWire and IOAudio kernel families ship for arm64e (Apple Silicon kernel caches, macOS 14.8.4 KDK), including the classic-DCL createLocalIsochPort.
E-6: an arm64e IOAudio driver must implement driverDesiresHiResSampleIntervals().
E-10: the 0.2.2 Swift 4.1 panel starts on Intel macOS 14.8.9 (demo mode).
E-12: the M-Audio MIDI plug-in is x86_64 + i386 with minimum 10.7 - no arm64, and 10.6 is unverified.
E-17 (R125): built with the macOS 15.2 SDK, the kext resolves 778 of 778 imports on the live 14.8.9 kernel (the reserved slots become the HiRes methods).
E-18 (R126): the Modern kext loads on 14.8.9 Intel and plays through the FW Audiophile (TX 46/46 ms, no late callback); one dropout during real use, the adapter's FireWire controller left PCI first (cause open).
R127: monitor law for phones only (outputs and aux out back on the official laws); the panel's About tab names the edition (OAEdition).
R128: package 0.3.0 per edition (Classic / Modern) with disk images; OS range enforced by the installer; Modern postinstall gates the kext with kmutil.
R129: one source, two builds (Classic 10.13 SDK, Modern 15.2 SDK); OA_BAND_MODERN is unused by the sources; docs/EDITIONS.md lists the differences and what is untested
R130 (2026-10-22): scope floor is 10.9; Legacy edition and band L dropped; tasks BC-1.3, 2.2, 3.4, 4.4, 4.5, 4.7, 6.3 cancelled (effort zeroed); DEC-1 answered b; DEC-2, 4, 6 moot
Note on D14: Sum of Tasks!I (min sessions) for this band. Edit the inputs in Tasks, not here.

## Tasks
ID | Phase | Band | Task | Acceptance (how we know it is done) | Depends on | Status | Who | Min sessions | Max sessions | Plan ref | Notes
BC-1.1 | 1 Static evidence | C | Symbol audit per kext build x OS: imports vs the KPI symbol sets and family exports of the oldest and newest OS of each band (SL rig 10.6.8 read-only copy, build PC 10.13.6, KDKs 10.9 / 11 / 15) | A table build x OS with zero unexplained missing symbols | DEC-1; SL rig reachable | Partly done | Claude | 1 | 2 | §7 BC-1 | 2026-10-21: E-1 (28 imports no reference build uses), E-3 (10.13.6 exports both lock names), E-4 (14.8.4 Intel: 2 of 777 missing = reserved slots 15/16). SL rig did not answer SSH.
BC-1.2 | 1 Static evidence | C | Confirm U-1, U-2, U-3, U-6 (K32 defaults, unsigned-kext policy per OS, kext location per OS, Tahoe ceiling) from Apple documentation, man pages and KDKs | Every OS_Matrix cell has a source; U-1/2/3/6 closed or re-labelled | — | Waiting decision | Claude | 0.5 | 1 | §3, §7 BC-1
BC-1.3 | 1 Static evidence | L | i386 (ILP32) audit of the kext: pointer/UInt32 casts, mach_vm sizes, user-client struct layouts for 32- and 64-bit tasks, format strings | List of findings with file:line; none left unclassified | DEC-1 = a; DEC-2 | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-1
BC-1.4 | 1 Static evidence | AS | Apple Silicon audit of the kext: 16 KiB pages (TPacketPool 4096 packing, 4 KiB meter page, FWSharedSync 0x1000), AbsoluteTime units, pointer authentication on DCL CallProc / FWFunctor, IOCreateThread, inTaskWithPhysicalMask under DART, driverDesiresHiResSampleIntervals | List of findings with file:line and the fix for each | DEC-3 | Waiting decision | Claude | 1 | 1.5 | §7 BC-1 | Sites already known: TPacketPool.cpp:15-34, FWBaseEngine.cpp:179, FWDCLProgram.cpp:284-477, FWAVCAudioDevice.cpp:212, FWBusReset.cpp:5
BC-1.5 | 1 Static evidence | C | Header compile of the kext per SDK (-fsyntax-only): 10.6 SDK, 10.13 SDK, 15.2 SDK -arch arm64e | Error list per SDK, each mapped to a BC-3 fix | DEC-6 (10.6 SDK) | Waiting decision | Claude | 0.5 | 1 | §7 BC-1
BC-1.6 | 1 Static evidence | M | Panel and Uninstaller API audit (availability per macOS version) | API list with the OS each needs | — | Done (static) | Claude | 0 | 0 | §2 E-11 | 2026-10-21: 5 panel APIs newer than 10.9; Swift floor 10.9
BC-1.7 | 1 Static evidence | C | MIDI plug-in audit (architectures, minimum OS) | Architectures and LC_VERSION_MIN known | — | Done (static) | Claude | 0 | 0 | §2 E-12 | 2026-10-21: x86_64 + i386, min 10.7. Open: U-7 (10.6), U-9 (Apple Silicon)
BC-2.1 | 2 Build system | C | Band-aware build files: kext/Makefile BAND=legacy¦main¦silicon (SDK, archs, min version, OA_BAND_* defines); helper universal; panel per slice | make BAND=... produces each slice; the 0.2.2 Main build is byte-identical in behaviour (same flags) | DEC-1, DEC-3, DEC-9 | Done (classic, modern; legacy not built) | Claude | 1 | 1 | §7 BC-2 | 2026-10-21: kext/Makefile BAND=classic¦modern (R125); panel Makefile BAND -> Info.plist OAEdition, build/<band>/ (R127); legacy not built, no arm64e
BC-2.2 | 2 Build system | L | Legacy toolchain probe (P-2): Xcode 9.4.1 clang/ld + MacOSX10.6.sdk (its i386 libkmod) for an i386 + x86_64 kext; fallback Xcode 4.6.3 on a 10.8 volume | An i386 + x86_64 kext links; kextutil -n -t passes on 10.6.8 | DEC-1 = a; DEC-6 | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-2
BC-2.3 | 2 Build system | AS | Silicon toolchain: arm64e kext + arm64 user space with the CLT 15.2 SDK (libkmod arm64e, E-13) or Xcode 12+ on another Mac | An arm64e kext and arm64 helper/panel build | DEC-3; DEC-10 | Waiting decision | Claude | 0.5 | 1 | §7 BC-2
BC-2.4 | 2 Build system | C | Merge and guards: lipo per component; per-slice LC_VERSION_MIN / LC_BUILD_VERSION guard; symbol-audit gate in the build; check-self-contained.sh for universal bundles | A wrong-band symbol or slice fails the build | BC-1.1, BC-2.1 | Waiting decision | Claude | 1 | 1.5 | §7 BC-2
BC-3.1 | 3 Kernel | C | One OS gate in base/ (version_major); re-label each 10.13-forced deviation (VerifyStreamFormats R68 and the others in CLAUDE.md) with the OS range that forces it | Every deviation comment names its OS range; conformance check passes | BC-2.1 | Waiting decision | Claude | 0.5 | 1 | §7 BC-3
BC-3.2 | 3 Kernel | M | Bind IOLockSleep/IOLockWakeup to the plain exported names (__asm label; 10.13.6 exports both, E-3) or use IOCommandGate::commandSleep; -D_FORTIFY_SOURCE=0 if U-5 fails | nm -u of the Main build has no _darwin14 symbol; BC-1.1 clean for 10.9 | BC-1.1 | Not needed on 11-15; only for 10.9-10.12 | Claude | 0.5 | 0.5 | §7 BC-3
BC-3.3 | 3 Kernel | M | Reserved IOAudioEngine slots 15/16 on 11-15 (E-4, U-11): confirm kmutil patches them; otherwise build an 11+ x86_64 slice with a new SDK (third bundle) | kextutil -n -t + a load on one Intel 11+ Mac, or the third bundle exists | BC-6.1 | Done (2026-10-21): 15.x SDK build loads on 14.8.9 (R126) | Claude | 0.5 | 1 | §7 BC-3 | The Modern band is built with the 15.x SDK (BAND=modern): 778/778 resolve (E-17) and it loads (E-18). No kmutil patching needed; the Modern edition is the separate 11+ build
BC-3.4 | 3 Kernel | L | Legacy build: fix what BC-1.5 / BC-1.3 found; Info.plist with KPI library names (per-arch keys only if needed, reference pattern OSBundleLibraries_x86_64) | Legacy kext links for i386 + x86_64; BC-1.1 clean for 10.6.8 | BC-2.2, BC-1.3, BC-1.5 | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-3
BC-3.5 | 3 Kernel | AS | Silicon build: implement driverDesiresHiResSampleIntervals (+ useHiResSampleInterval / calculateSampleTimeoutHiRes as documented) and the BC-1.4 fixes; comments say 'forced by the arm64 IOAudioEngine header' | arm64e kext links; BC-1.1 clean against an arm64e KDK | BC-1.4, BC-2.3 | Waiting decision | Claude | 2 | 4 | §7 BC-3
BC-3.6 | 3 Kernel | C | Bundle layout per band: same bundle id and personalities; Main file = x86_64 + arm64e | Both bundles pass plutil and kextutil -n -t on a host of their band | BC-3.2, BC-3.4, BC-3.5 | Not needed (two kext builds, DEC-5 = b) | Claude | 0.5 | 0.5 | §7 BC-3
BC-4.1 | 4 User space | C | Helper universal: i386 + x86_64 (Xcode 9.4.1, min 10.6) + arm64 (min 11), lipo; no API change (E-14) | lipo -archs shows the slices; each slice's min version matches its band | BC-2.1 | Waiting decision | Claude | 0.5 | 0.5 | §7 BC-4
BC-4.2 | 4 User space | M | Swift panel to 10.9: #available fallbacks for the 5 APIs (E-11), deployment target 10.9; Uninstaller likewise | Typecheck at -target x86_64-apple-macosx10.9; --demo --snapshot PNGs unchanged on 10.13 | BC-2.1 | Not needed on 11-15 (panel runs on 14.8.9); only for 10.9-10.12 | Claude | 1 | 2 | §7 BC-4
BC-4.3 | 4 User space | AS | Panel and Uninstaller arm64 slice: same sources with a Swift 5 compiler (-swift-version 4.2 if needed), lipo with the Swift 4.1 x86_64 slice; bundle-swift-runtime.sh universal-aware | Universal app passes check-self-contained; --demo --snapshot on arm64 and x86_64 | BC-2.3, BC-4.2 | Waiting decision | Claude | 0.5 | 1 | §7 BC-4
BC-4.4 | 4 User space | L | Panel port to Objective-C (DEC-4 a), file by file, host tests ported; replaces the Swift panel everywhere (one universal binary, no Swift runtime) | Demo snapshots match the Swift panel's on 10.13; app launches on 10.6.8 | DEC-4 = a | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-4 | Largest single item: 5,925 Swift lines (E-16)
BC-4.5 | 4 User space | L | Uninstaller for 10.6-10.8 (Obj-C with BC-4.4, or an AppleScript applet) | Runs on 10.6.8 and removes every listed path | BC-5.3 | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-4
BC-4.6 | 4 User space | AS | MIDI clone plug-in mirroring the M-Audio plug-in (A3 decompiles, user-client selectors 500-507), universal | MIDI in/out through the clone on one Intel Mac matches the original (midiprobe) | DEC-8 | Waiting decision | Claude | 4 | 8 | §7 BC-4
BC-4.7 | 4 User space | L | MIDI on 10.6: check the 1.11.2 plug-in's imports against the 10.6.8 frameworks (U-7); otherwise ship the clone there | U-7 closed | BC-1.1 | Cancelled (scope, 2026-10-22: floor 10.9) | Claude | 0 | 0 | §7 BC-4
BC-5.1 | 5 Installer | C | distribution.xml: min 10.6.8 (or the DEC-1 floor), hostArchitectures i386,x86_64,arm64, OS-conditional choices for the kext bundle/location and MIDI plug-in | pkgutil --payload-files per choice; Installer picks the right bundle on each band | DEC-1, DEC-5 | Done for Classic + Modern (per-edition distribution.xml, R128) | Claude | 0.5 | 1 | §7 BC-5 | 2026-10-21 (R128): one package per edition instead of OS-conditional choices (DEC-5 b): Classic min 10.13 before 11.0, Modern min 11.0 before 16.0; checked with installer -volinfo on 14.8.9 and 10.13.6
BC-5.2 | 5 Installer | C | postinstall per band: caches (touch /S/L/E + kextcache on L; -system-caches on M; kmutil flow + approval/restart message on M11/AS); keep the kextutil -t -n gate; MIDIServer restart | Script review per band; the gate runs on all bands | BC-5.1 | Done for Classic + Modern (R128); Modern uninstall unverified | Claude | 1 | 1.5 | §7 BC-5 | 2026-10-21 (R128): postinstall-modern = kmutil import gate (shipped imports.txt) + kmutil load -p + helper + agent + MIDIServer; Classic postinstall unchanged; Legacy not done
BC-5.3 | 5 Installer | C | uninstall.sh: add /System/Library/Extensions/OpenAudioBeBoBMAFW.kext and every new path (all-paths-ever rule kept) | Dry-run listing covers every payload path of every band | BC-5.1 | Done for Classic + Modern (kmutil rebuild branch, unverified) | Claude | 0.5 | 0.5 | §7 BC-5 | 2026-10-21 (R128): uninstall.sh runs kmutil rebuild on 11+ (unverified), kextcache on 10.x
BC-5.4 | 5 Installer | C | Installer pages + README: per-band prerequisites (10.10 boot-arg, 10.11+ SIP, 11+ approval, Apple Silicon Permissive Security) - documentation only | Text reviewed by the user | BC-1.2 | Done for Classic + Modern (Requirements tables, R128) | Claude | 0.5 | 0.5 | §7 BC-5 | 2026-10-21 (R128): Requirements per edition on the installer pages and dmg backgrounds; README pending
BC-6.1 | 6 On-device (on request) | M | P-1: Main kext on one Intel 11-15 Mac (kextutil -n -t, load, CoreAudio, play/record, panel); also U-8, U-11, U-12 with the Legacy build | Results recorded in a dated run log | DEC-7; user request | Partly done (Audiophile plays on 14.8.9; FW1814, record, MIDI, rates open) | User + Claude | 1 | 1 | §7 BC-6, §8 | A panic reboots the host ¦ 2026-10-21 (R126): load + play on 14.8.9 Intel with the FW Audiophile (E-18); one dropout in real use (adapter controller left PCI, cause open). Open: record/RX, panel controls (U-8), MIDI, rates, FW1814, unload, sleep
BC-6.2 | 6 On-device (on request) | M | Main kext on one of 10.9-10.12 | Dated run log | DEC-7; user request | On request | User + Claude | 1 | 1 | §7 BC-6
BC-6.3 | 6 On-device (on request) | L | Legacy kext on 10.6.8, K32 and K64, on a volume other than the SL rig's reference install | Dated run log | DEC-7; user request | Cancelled (scope, 2026-10-22: floor 10.9) | User + Claude | 0 | 0 | §7 BC-6
BC-6.4 | 6 On-device (on request) | AS | Apple Silicon with the TB3->TB2 and TB->FW800 adapters (U-10, U-14) | Dated run log | DEC-3, DEC-7; hardware | Blocked (hardware) | User + Claude | 1 | 2 | §7 BC-6 | No Apple Silicon Mac in the inventory
BC-7.1 | 7 Release | C | README compatibility table (verified / untested per band), NOTICE, CHANGELOG, VERSION (0.3.0 proposed), docs/ARCHITECTURE_MAFW_v2.md, /close-item | README states each band's status honestly | all of the chosen scenario | Waiting decision | Claude | 1 | 1 | §7 BC-7

## Decisions
ID | Question | Options | Recommendation | Why / consequence | Gates | Status | Answer (user, with date)
DEC-1 | Lowest OS to support | a) 10.6.8 (as asked; adds band L) b) 10.9 (no old toolchain; Swift panel kept) c) keep 10.13, extend upward only | b now; a later if wanted | Band L costs 11.5-21.5 sessions, mostly the panel port; official M-Audio drivers already run 10.6.8 (v1.9, SL rig) and, per B3, up to 10.11 | BC-1.3, BC-2.2, BC-3.4, BC-4.4/4.5/4.7, BC-5.1, BC-6.3 | Answered | b) lowest OS 10.9 (user, 2026-10-22: "the older ones work well on official drivers")
DEC-2 | 32-bit kernel (i386 kext slice) for 10.6/10.7 Macs booted K32 | yes / no | yes if DEC-1 = a | Without it, 10.6 Macs must boot the 64-bit kernel; 32-bit-EFI Macs cannot (U-1) | BC-1.3, BC-2.2, BC-3.4 | Answered | Moot (no i386 slice; Legacy dropped, 2026-10-22)
DEC-3 | Apple Silicon in scope | yes (Apple Silicon Mac + TB3->TB2 + TB->FW800 adapters, Permissive Security, MIDI clone) / no | yes as stage S2 once hardware exists | Kernel families exist on arm64e in macOS 14.8.4 (E-5); hardware path unproven (U-10) | BC-1.4, BC-2.3, BC-3.5, BC-4.3, BC-4.6, BC-6.4 | Open
DEC-4 | Control panel on 10.6-10.8 | a) Objective-C port: one panel for every OS b) Swift 10.9+ plus a separate Obj-C legacy panel c) no panel on 10.6-10.8 | a if DEC-1 = a | b doubles the UI code; c loses mixer, routing, clock and firmware-check UI on 10.6-10.8 | BC-4.4, BC-4.5 | Answered | Moot (Swift panel kept; no Obj-C port; 2026-10-22)
DEC-5 | Packaging | a) one package, OS-conditional choices b) three editions (Legacy / Classic / Modern) | a | Same code either way; a = one download and one version per release | BC-5.1 | Answered | b) three editions: Legacy 10.6.8-10.8.5, Classic 10.9-10.15, Modern 11-15 (user, 2026-10-21, R125; plan v2 §11a)
DEC-6 | Source of the 10.6 SDK (band L) | Apple developer downloads (Xcode 3.2.6 / 4.x, the user's Apple ID) | user action | Modern SDKs have no i386 libkmod (E-13) and their x86_64 headers produce symbols 10.6 lacks (E-1, E-2) | BC-1.5, BC-2.2 | Answered | Moot (no 10.6 SDK needed; 2026-10-22)
DEC-7 | Test hosts per band, and whether any BC-6 check happens | SL rig second volume (10.6.8); iMac11,2 extra volume; MacBookAir5,1 (10.14/10.15); dev Mac (11-14); none | the user's call | No formal testing (R123): bands nobody loaded ship labelled untested | BC-6.1 to BC-6.4 | Open | Partly (user, 2026-10-21): the dev Mac (MacBookAir7,2, 14.8.9) for Modern Intel; other bands open
DEC-8 | MIDI on Apple Silicon | a) clone plug-in (Apple Silicon only) b) clone everywhere c) no MIDI on Apple Silicon | a | An arm64e MIDIServer cannot load the x86_64/i386 M-Audio plug-in in-process (U-9); a keeps Intel unchanged | BC-4.6 | Open
DEC-9 | Where the work lives; version numbers | branch of openaudio-mafw-bebob / new folder; package 0.3.0, driver 0.3.0 | branch; 0.3.0 | openaudio-fw1814/ stays frozen; band builds share one tree | BC-2.1, BC-7.1 | Answered | Same tree openaudio-mafw-bebob, BAND=classic¦modern; package 0.3.0, driver 0.2.1 (R128, 2026-10-21)
DEC-10 | Build arm64e/arm64 slices on the dev Mac | allow CLT builds there (CLAUDE.md keeps it edit-only) / use another Mac | the user's call | The dev Mac's CLT 15.2 SDK has arm64e libkmod (E-13) | BC-2.3 | Answered | Modern kext is built on the dev Mac (CLT 15.2 SDK, R125-R128); Apple Silicon slices not built

## OS_Matrix
OS | Name | Darwin (version_major) | Band | Kernel arch | Kext build | Kext location | Unsigned-kext prerequisite | Cache / load tool | IOAudioFamily | IOFireWireFamily | AppleFWAudio.kext | Panel | MIDI plug-in | Project host | Facts status | Source
10.6.8 | Snow Leopard | 10 | L | i386 (K32, default on most Macs, U-1) or x86_64 | Legacy i386 + x86_64 | /System/Library/Extensions (U-3) | none (U-2) | touch /S/L/E + kextcache | — | — | unverified | Obj-C port or none (DEC-4) | original if U-7 holds, else clone | SL rig (keep v1.9 install: separate volume); iMac11,2 | Unverified except: v1.9 runs here (SL rig) | U-1, U-2, U-3, U-7
10.7.5 | Lion | 11 | L | x86_64 (K32 on some Macs, U-1) | Legacy i386 + x86_64 | /System/Library/Extensions (U-3) | none (U-2) | touch /S/L/E + kextcache | — | — | unverified | Obj-C port or none | original (min 10.7, E-12) | iMac11,2; MacBookAir5,1 (recalled ranges) | Unverified | U-1, U-2, U-3
10.8.5 | Mountain Lion | 12 | L | x86_64 | Legacy i386 + x86_64 (x86_64 used) | /System/Library/Extensions (U-3) | none (U-2) | touch /S/L/E + kextcache | — | — | unverified | Obj-C port or none | original | iMac11,2; MacBookAir5,1 | Unverified | U-2, U-3
10.9.5 | Mavericks | 13 | M | x86_64 | Main x86_64 (after BC-3.2; U-4) | /Library/Extensions | unverified (U-2) | kextcache -system-caches | — | — | unverified | Swift (after BC-4.2) | original | iMac11,2; MacBookAir5,1 | Unverified | U-2, U-4, U-5
10.10.5 | Yosemite | 14 | M | x86_64 | Main x86_64 | /Library/Extensions | boot-arg kext-dev-mode=1 (U-2) | kextcache -system-caches | — | — | unverified | Swift (after BC-4.2) | original | iMac11,2; MacBookAir5,1 | Unverified | U-2, U-5
10.11.6 | El Capitan | 15 | M | x86_64 | Main x86_64 | /Library/Extensions | SIP off or --without kext (U-2) | kextcache -system-caches | — | — | unverified | Swift (after BC-4.2) | original | iMac11,2; MacBookAir5,1 | Unverified | U-2, U-5
10.12.6 | Sierra | 16 | M | x86_64 | Main x86_64 | /Library/Extensions | SIP off (U-2) | kextcache -system-caches | — | — | unverified | Swift (after BC-4.2) | original | iMac11,2; MacBookAir5,1 | Unverified | U-2, U-5
10.13.6 | High Sierra | 17 | M | x86_64 | Main x86_64 (= today's build) | /Library/Extensions | SIP off (verified by the project) | kextcache -system-caches | 206.5 (E-8) | 4.7.2 (E-8) | present (E-8) | Swift (today) | original (today) | build PC; MacBook Air (today) | Verified (0.2.2 in use) | E-3, E-8, E-9
10.14.6 | Mojave | 18 | M | x86_64 | Main x86_64 | /Library/Extensions | SIP off (U-2) | kextcache -system-caches | — | — | unverified | Swift | original | MacBookAir5,1 | Unverified | U-2
10.15.7 | Catalina | 19 | M | x86_64 | Main x86_64 | /Library/Extensions (system volume read-only) | SIP off (U-2) | kextcache -i / | — | — | unverified | Swift | original | MacBookAir5,1 | Unverified | U-2
11 (Intel) | Big Sur | 20 | M11 | x86_64 | Modern x86_64 (15.x SDK) | /Library/Extensions -> auxiliary KC | SIP off; approval + restart (U-2) | kmutil (kextutil -n -t for the gate) | — | — | unverified | Swift (E-10 on 14) | original (U-8) | dev Mac (supports up to 12, recalled) | Unverified | U-2, U-8, U-11
12 (Intel) | Monterey | 21 | M11 | x86_64 | Modern x86_64 (15.x SDK) | /Library/Extensions -> auxiliary KC | SIP off; approval + restart (U-2) | kmutil | — | — | unverified | Swift | original (U-8) | dev Mac | Unverified | U-2, U-8, U-11
13 (Intel) | Ventura | 22 | M11 | x86_64 | Modern x86_64 (15.x SDK) | /Library/Extensions -> auxiliary KC | SIP off; approval + restart (U-2) | kmutil | — | — | unverified | Swift | original (U-8) | dev Mac (non-standard install) | Unverified | U-2, U-8, U-11
14 (Intel) | Sonoma | 23 | M11 | x86_64 | Modern x86_64 (15.x SDK): loads and plays (E-18) | /Library/Extensions -> auxiliary KC | SIP off; approval + restart (U-2) | kmutil | 540.3 (E-7) | 4.8.3 (E-7) | absent (E-7) | Swift (demo runs, E-10) | original (U-8) | dev Mac 14.8.9 (non-standard install) | Partly verified (static) | E-4, E-7, E-10, U-11
15 (Intel) | Sequoia | 24 | M11 | x86_64 | Modern x86_64 (15.x SDK) | /Library/Extensions -> auxiliary KC | SIP off; approval + restart (U-2) | kmutil | — | — | unverified | Swift | original (U-8) | none | Unverified | U-2, U-8, U-11
11-15 (Apple Silicon) | Big Sur ... Sequoia | 20-24 | AS | arm64e | Main arm64e slice (BC-3.5) | /Library/Extensions -> auxiliary KC | Permissive Security + user-managed kexts; approval + restart (U-2) | kmutil | arm64e build exists (E-5) | arm64e build exists (E-5) | absent in kernelcache manifests (E-5 lists no AppleFWAudio) | arm64 slice (BC-4.3) | clone (DEC-8, U-9) | none (needs hardware + 2 adapters) | Families verified present (static); hardware path unverified | E-5, E-6, U-9, U-10, U-14
26 | Tahoe | 25 | — | — | out of scope | — | — | — | — | no FireWire stack (U-6) | — | — | — | — | Unverified (macfw statement) | U-6

## Feature_by_OS
Feature | 10.6.8-10.8.5 (L) | 10.9-10.12 (M) | 10.14-10.15 (M) | 11-15 Intel (M11) | 11-15 Apple Silicon (AS) | Evidence / settle by
Audio I/O, all rates 44.1-192 kHz, S/PDIF / ADAT / S/MUX | Same (v1.9 does it on 10.6.8; ours unverified) | Same (unverified) | Same (unverified) | Same (unverified) | unverified | U-10, U-11, U-13, U-14
32-bit kernel (K32) Macs | needs the i386 slice (DEC-2) | n/a | n/a | n/a | n/a | U-1
Mixer, routing, levels, encoders, helper settings replay | Same | Same | Same | Same | unverified | E-14
Meters (shared 4 KiB page) | Same | Same | Same | Same | 16 KiB page review | U-14, BC-1.4
MIDI in/out | Same if U-7 holds, else clone | Same | Same | Same (U-8) | LOST unless the clone exists | U-7, U-9, DEC-8
Control panel | LOST if DEC-4 = c; = with the Obj-C port | Same (fallbacks, E-11) | Same | Same (E-10, demo) | Same with arm64 slice | E-10, E-11
Panel: dark vibrant title bar | lost (10.10+) | lost on 10.9 | Same | Same | Same | E-11
Panel: tabular-digit system font | fallback | fallback on 10.9-10.10 | Same | Same | Same | E-11
Panel: GPU-only meter updates | fallback on 10.6-10.7 (CPU drawing) | Same | Same | Same | Same | wantsUpdateLayer 10.8+
Panel: Retina | lost on 10.6 (10.7.3+) | Same | Same | Same | Same | recalled
Panel: Big Meter full screen | lost on 10.6 (10.7+) | Same | Same | Same | Same | recalled
Status menu, launch at login | fallback (legacy NSStatusItem API) | fallback on 10.9 | Same | Same | Same | E-11
CoreAudio listeners | fallback on 10.6 (C callbacks) | Same | Same | Same | Same | AudioHardware.h:397 (10.7)
Firmware check window (read-only) | Same with the port | Same | Same | Same | Same
Uninstall app | needs a port | fallbacks | Same | Same | arm64 slice or Rosetta | E-11
Install steps | kext in /System/Library/Extensions; no prerequisite | 10.10 boot-arg; 10.11+ SIP off | SIP off | SIP off + approval + restart | Permissive Security + approval + restart | U-2, U-3

## Components
Component | Today (0.2.2) | Band L (10.6.8-10.8.5) | Band M (10.9-10.15) | Band M11 (11-15 Intel) | Band AS (11-15 Apple Silicon) | Builds needed | Tasks
Kernel extension | x86_64, Xcode 9.4.1, 10.13 SDK, min 10.13 (E-9) | Legacy build: i386 + x86_64, 10.6 SDK | Main x86_64 (10.13 SDK) + BC-3.2 | same Main x86_64 slice (U-11) | arm64e slice in the Main file, 15 SDK, + BC-3.5 | 2 (Legacy, Main); 1 if U-12 holds; 3 if BC-3.3 fails | BC-1.1/1.3/1.4/1.5, BC-2.x, BC-3.x
Helper daemon (C) | x86_64, min 10.13 | i386 + x86_64 slice, min 10.6 | same | same | arm64 slice, min 11 | 1 universal binary | BC-4.1
Control panel | Swift 4.1, x86_64, bundled runtime, min 10.13 | Obj-C port (DEC-4 a) or none | Swift min 10.9 (BC-4.2) or the Obj-C port | same | arm64 slice (Swift 5) or the Obj-C port | 1 (Obj-C port) or 1 Swift universal + nothing on L | BC-4.2, BC-4.3, BC-4.4
Uninstall app | Swift 4.1, x86_64 | Obj-C / AppleScript | Swift min 10.9 | same | arm64 slice | 1-2 | BC-4.2, BC-4.3, BC-4.5
CoreMIDI plug-in | M-Audio 1.11.2 original, x86_64 + i386, min 10.7 (E-12) | original if U-7 holds, else clone | original | original (U-8) | clone (DEC-8) | 1 (original) + 1 (clone) if AS | BC-4.6, BC-4.7
Installer package | min 10.13, hostArchitectures x86_64 (E-9) | choice: Legacy kext -> /System/Library/Extensions | choice: Main kext -> /Library/Extensions | same + kmutil message | same + Permissive Security text | 1 package (Option A) | BC-5.x
Disk image | UDZO + HFS+ (E-15) | opens on 10.6 | same | same | same | 1 | —
Bench tools (not shipped) | C, x86_64 | rebuild per band only when needed | same | same | arm64 if needed | on demand | —

## Evidence
ID | Kind | Statement | How checked / how to settle | File or source | Date | Feeds
E-1 | Checked | 0.2.2 kext imports 777 symbols; 28 imported by no reference build, incl. _IOLockSleep_darwin14, _IOLockWakeup_darwin14, IOService::configureReport/updateReport, ___memmove_chk, ___strlcat_chk | nm -u of the 0.2.2 payload and of v1.9 / v1.10.5 / v1.11.3 | evidence/kext-0.2.2-imports*.txt | 2026-10-21 | §1, BC-1.1, BC-3.2
E-2 | Checked | Modern SDKs alias IOLockSleep / IOLockSleepDeadline / IOLockWakeup to _darwin14 names on x86_64 regardless of deployment target | Read the SDK headers | MacOSX13.3.sdk sys/cdefs.h:514-519; IOKit/IOLocks.h:129,132,134 | 2026-10-21 | BC-3.2
E-3 | Checked | 10.13.6 KPI symbol sets export both plain and _darwin14 lock names, ___memmove_chk, ___strlcat_chk, _version_major, _kernel_thread_start, _thread_call_allocate, _IOCreateThread | read-only nm on the build PC | evidence/buildpc-10.13.6-kpi-exports.txt | 2026-10-21 | BC-3.1, BC-3.2
E-4 | Checked | macOS 14.8.4 Intel: all but 2 of 777 imports defined; missing IOAudioEngine::_RESERVEDIOAudioEngine15/16 (now calculateSampleTimeoutHiRes / useHiResSampleInterval) | KDK 14.8.4 kernel + family dSYMs; 15.2 SDK IOAudioEngine.h:389,403,431-432 | evidence/kext-0.2.2-vs-macos-14.8.4-x86_64.txt | 2026-10-21 | BC-3.3, U-11
E-5 | Checked | IOFireWireFamily, IOFireWireAVC, IOAudioFamily, IOFireWireSBP2 built for arm64e; Apple Silicon kernelcache manifests list them + AppleFWOHCI; arm64e IOFireWireFamily defines createLocalIsochPort (classic DCL) | KDK 14.8.4 dSYM lipo -archs; manifests; nm | evidence/kdk-14.8.4-families-arm64e.txt | 2026-10-21 | DEC-3, BC-3.5
E-6 | Checked | ARM-only pure virtual IOAudioEngine::driverDesiresHiResSampleIntervals() must be implemented by ARM subclasses | Read the SDK header | MacOSX15.2.sdk IOKit/audio/IOAudioEngine.h:928-943 | 2026-10-21 | BC-3.5
E-7 | Checked | macOS 14.8.9: IOFireWireLib / IOFireWireAVCLib / MIDIServer are x86_64 + arm64e; AppleFWAudio.kext absent; IOAudioFamily 540.3, IOFireWireFamily 4.8.3, IOFireWireAVC 4.2.8 | lipo -archs, Info.plist on the dev Mac | dev Mac | 2026-10-21 | OS_Matrix
E-8 | Checked | 10.13.6: IOAudioFamily 206.5, IOFireWireFamily 4.7.2, IOFireWireAVC 4.2.6; AppleFWAudio.kext present | read-only on the build PC | evidence/buildpc-10.13.6-kpi-exports.txt | 2026-10-21 | OS_Matrix
E-9 | Checked | All 0.2.2 binaries x86_64 only; helper/panel LC_VERSION_MIN 10.13; installer min 10.13, hostArchitectures x86_64 | lipo, otool -l; distribution.xml.in:6-7 | dist/OA-BeBoB-MAFW-0.2.2.pkg | 2026-10-21 | BC-2.x, BC-5.1
E-10 | Checked | 0.2.2 panel starts and renders 8 demo snapshots on Intel macOS 14.8.9 (demo mode only) | --demo --snapshot on the dev Mac | evidence/panel-0.2.2-demo-macos-14.8.9.txt | 2026-10-21 | M11 panel
E-11 | Checked | Panel APIs newer than 10.9: labelWithString 10.12, monospacedDigitSystemFont 10.11, vibrantDark 10.10, NSStatusItem.button 10.10, labelColor 10.10; listener blocks 10.7; Swift floor 10.9 | API_AVAILABLE in the 15.2 SDK headers; grep of Sources/ | Widgets.swift:11, Theme.swift:62,173, StatusMenu.swift:35,105,114 | 2026-10-21 | BC-4.2, DEC-4
E-12 | Checked | Reference builds: v1.11.3 kext x86_64 only (OSBundleLibraries + OSBundleLibraries_x86_64); v1.10.5 x86_64 + i386 + ppc; v1.9 i386 + x86_64; MIDI plug-in 1.11.2 x86_64 + i386, LC_VERSION_MIN 10.7 | lipo, otool -l, PlistBuddy | _extracted/, _refs/sl-v1.9, _vendor/README.md | 2026-10-21 | BC-3.4, BC-4.7
E-13 | Checked | CLT SDKs 13-15.2 on the dev Mac; 15.2 libkmod x86_64/x86_64h/arm64e; cc_kext i386/x86_64/arm64/arm64e; no i386 libkmod in modern SDKs | lipo -archs | dev Mac | 2026-10-21 | BC-2.2, BC-2.3
E-14 | Checked | Helper uses only 10.0-10.4-era IOKit / CF / SystemConfiguration APIs | grep of firmware-helper/*.c | firmware-helper/ | 2026-10-21 | BC-4.1
E-15 | Checked | Disk image UDZO + HFS+ | read the settings | installer/dmg-settings.py:7-8 | 2026-10-21 | Components
E-16 | Checked | Panel 5,925 lines of Swift (+ ~120 Uninstaller); helper 457 lines of C | wc -l | control-panel/Sources, firmware-helper | 2026-10-21 | BC-4.4
U-1 | Unverified | 10.6 boots K32 on most Macs; 10.7 on some; 32-bit-EFI Macs cannot boot K64 | uname -v per target; Apple notes | BC-1.2 |  | DEC-2
U-2 | Unverified | Unsigned-kext policy per OS (10.10 kext-dev-mode, 10.11+ SIP, 11+ AuxKC approval, Apple Silicon Permissive Security); 10.13.6 row verified by the project | Apple docs, man kmutil/kextutil | BC-1.2 |  | OS_Matrix, BC-5.4
U-3 | Unverified | /Library/Extensions is scanned only from 10.9 | Apple docs | BC-1.2 |  | BC-5.1
U-4 | Unverified | IOReporting (configureReport/updateReport) exists from 10.9 - the Main build's floor | 10.9 symbol set / KDK | BC-1.1 |  | DEC-1
U-5 | Unverified | ___memmove_chk / ___strlcat_chk exported on 10.9-10.12 | symbol sets; or -D_FORTIFY_SOURCE=0 | BC-1.1 |  | BC-3.2
U-6 | Unverified | macOS 26 Tahoe has no FireWire stack (ceiling = 15) | macfw statement; a Tahoe KDK | docs/MACOS12_PORT_PERSPECTIVE.md §1-2 |  | scope
U-7 | Unverified | The 1.11.2 MIDI plug-in (min 10.7) runs on 10.6.8 | imports vs 10.6.8 frameworks | BC-4.7 |  | Band L MIDI
U-8 | Unverified | x86_64 panel works against the real kext on 11-15 | BC-6.1. 2026-10-21: the panel starts and opens the vendor user client against the real kext on 14.8.9 (R126); controls and meters not exercised | BC-6.1 |  | M11
U-9 | Unverified | CoreMIDI on Apple Silicon can host an x86_64-only driver plug-in | one Apple Silicon run or Apple docs | — |  | DEC-8
U-10 | Unverified | FireWire works on Apple Silicon through TB3->TB2 + TB->FW800 adapters | BC-6.4 | BC-6.4 |  | DEC-3
U-11 | Unverified | kxld / kmutil patch the reserved-slot vtable entries 15/16 of a 10.13-SDK kext | Moot for the Modern edition: the 15.x SDK build is used instead (E-17, E-18); patching of a 10.13-SDK build never tried | BC-6.1 |  | BC-3.3
U-12 | Unverified | An old-SDK x86_64 slice loads and runs on 10.9-15 (would allow one kext bundle) | BC-6.1 with the Legacy build | BC-6.1 |  | Option A'
U-13 | Unverified | 10.6 HAL behaviour with our 10.13-driven deviations (VerifyStreamFormats, rate changes through CoreAudio) | BC-6.3 | BC-6.3 |  | RK-1
U-14 | Unverified | DCL ring, TPacketPool (4 KiB packing, 32-bit mask) and 4 KiB meter page on Apple Silicon (16 KiB pages, DART, 24 MHz timebase, PAC) | BC-1.4 static, BC-6.4 | BC-1.4 |  | BC-3.5
E-17 | Checked | 14.8.9 Intel: shipped 0.2.2 kext resolves 775/777 (only _RESERVEDIOAudioEngine15/16 missing); the same sources built with MacOSX15.2.sdk resolve 778/778 | kmutil libraries -p <kext> -a x86_64 -z on the dev Mac | evidence/kext-0.2.2-kmutil-libraries-macos-14.8.9.txt | 2026-10-21 | BC-3.3, U-11
E-18 | Checked | Modern kext (15.2 SDK) loads on 14.8.9 Intel, attaches the FW Audiophile through the TB-FW adapter and plays (user heard it; TX 46/46 ms, no CLIP jump); one dropout in real use, adapter FireWire controller left PCI first, cause open | Dev Mac run: kmutil showloaded, ioreg trace, say -a, maprop MADebugTxStats, log show | evidence/modern-kext-first-run-audiophile-macos-14.8.9.txt; evidence/modern-kext-dropout-macos-14.8.9-1941.txt | 2026-10-21 | BC-6.1, RK-4, RK-6

## Risks
ID | Risk | Bands | Likelihood (estimate) | Impact (estimate) | Mitigation | Task
RK-1 | 10.6 HAL / IOAudioFamily behave differently from 10.13 (U-13) | L | Medium | High | Decompile-and-diff first (standing method lesson); BC-6.3 | BC-6.3
RK-2 | A 10.13-forced deviation misbehaves on another IOAudioFamily version (206.5 vs 540.3) | all | Medium | Medium | BC-3.1 gates each deviation by OS range | BC-3.1
RK-3 | kmutil does not patch reserved slots 15/16 | M11 | Low | Medium | Done: the Modern edition is built with the 15.x SDK (E-17, E-18) | BC-3.3
RK-4 | Classic DCL from the kernel fails on 11-15 (symbol present on x86_64 and arm64e, E-4/E-5) | M11, AS | Low (Intel TX runs on 14.8.9, E-18) | High | BC-6.1 decides it early | BC-6.1
RK-5 | 16 KiB pages / DART / timebase break the DMA ring or meter page | AS | Medium | High | BC-1.4, BC-3.5 | BC-3.5
RK-6 | FireWire through the adapter chain unreliable; bus power short for the Audiophile | AS, M11 | Medium | High | BC-6.4; 2026-10-21: one dropout on Intel 14.8.9 with the adapter, interface bus-powered (R126; user suspects a bad contact) | BC-6.4
RK-7 | A panic reboots the test host; on Apple Silicon recovery needs recoveryOS | all | Medium | Medium | Say so before any load (hardware etiquette); §8 | BC-6.x
RK-8 | Three toolchains per release (Xcode 9.4.1, 10.6 SDK, CLT / Xcode 12+) | all | High | Low | BC-2 scripts; record toolchain versions in CHANGELOG | BC-2.x
RK-9 | Permissive Security lowers the whole Mac's security | AS | High | Medium | User's choice, stated in the installer pages | BC-5.4
RK-10 | Panel port introduces UI regressions | L | Medium | Medium | Port file by file against the --demo --snapshot PNGs | BC-4.4
RK-11 | Original MIDI plug-in fails on 10.6 (min 10.7) | L | Medium | Low | BC-4.7 -> clone | BC-4.7
RK-12 | Most bands ship untested (R123) | all | High | Medium | README marks each band; on-device checks only on request | BC-7.1

## Legend
Legend
Bands
C | Common: needed in every scenario
M | Main: Intel 10.9-15 (M11 = the same build on 11-15)
AS | Apple Silicon 11-15
L | Legacy: 10.6.8-10.8.5
Scenarios
S1 | Intel 10.9-15 = C + M
S2 | S1 + Apple Silicon = C + M + AS
S3 | S2 + 10.6.8-10.8.5 = C + M + AS + L (the full request)
Task status values
Waiting decision | Gated by a DEC-n in the Decisions tab
Partly done / Done (static) | Static work done on 2026-10-21 (nothing loaded)
On request | On-device check; runs only if the user asks (no formal testing, R123)
Blocked (hardware) | Needs hardware the project does not have
Editing
Blue text | Inputs you may change: task status, min/max sessions, risk ratings
Yellow cells | Decision answers (Decisions!H)
Black text | Fixed text or formulas (Dashboard totals refresh from Tasks)
Units
Session | One working session, as in docs/BUILD_AUDIOPHILE_PLAN_v2.md §8. Every effort figure is an estimate.
Evidence ids | E-n checked on 2026-10-21; U-n unverified, with the check that settles it
Plan | BROAD_COMPATIBILITY_PLAN_v1.md (same folder); a new version gets new files (_v2)